## Completed
User Side
SR. No. | Detail | Status
1 | Home | Completed
2 | About Us | Completed
3 | Gallery | Completed
4 | Member Directory - Listing | Completed
5 | Executive Commitee - Listing | Completed
6 | Society Inquiry | Completed
7
8
9
10
11
12
Admin Side
1 | Society Home | Completed
2 | Member Directory (Existing , New) - Listing, Add, Delete, Merge, Split, Replace, Import Excel (Ordered file, Unordered File) | Completed
3 | Executive Commitee - Create, Delete committee, Create member, add committee member | Completed
4 | About Us | Completed
5 | Society Inquiry- Listing | Completed
6 | Create Registration | Completed
7
8
9
10
11

## Pending
User Side | [5 empty] | Status Date
SR. No. | Detail | Status | Required Estimated | Start Date | End Date | 2021-06-17 | 2021-06-18
1 | Registration | Inprogress | 8 Hrs | 2021-06-04 | 2021-06-04 | InProgess
2 | Registration- Download offline form | Waiting for client confirmation |  |  |  | InProgess
3 | End user login - OTP Configuration | Waiting for client confirmation
4 | Access Management | New | 20 Hrs | 2021-06-16 | 2021-06-18 | InProgess | Done (Ex.Committee, Member, Home, View)
5
6
7
8
9
10
11
12
Admin Side
1 | Edit Member | Inprogress | 24 Hrs | 2021-06-06 | 2021-06-08 | Done | Pending Dynamic field binding in required document
2 | Executive Committee- Assign Module | Inprogress | 12 Hrs | 2021-06-09 | 2021-06-10 | Done
3 | Send email for society inquiry response | Inprogress | 6 Hrs | 2021-06-10 | 2021-06-11
4 | Access Management | New | 24 Hrs | 2021-06-11 | 2021-06-16 | Done
5 | Create domain for society | Analysis
6 | Account Info- Payment configuration | Requirement Clearification
7 | Download | Requirement Clearification
8 | Election | Requirement Clearification
9 | Creator view | Requirement Clearification
10 | End user view | Requirement Clearification
11 | Nominee view | Requirement Clearification
12
13
14
15
Note: Deisgn changes panding
Pending dynamic field binding in required document section of member